## Sprint Backlog
Ticket ID | Epic | Task Title | Description | Priority | Assignee | Status | Sprint | Story Points | Start Date | End Date | Dependencies | Comments
OSS-1 | Project Setup | Define Seed Library Dataset | Create representative seed dataset of libraries used by the organization | High | Harsh | Done | Week 1 | 3
OSS-2 | Project Setup | Create GCP Project | Setup Google Cloud project for the pipeline environment | High | Harsh | Done | Week 1 | 2
OSS-3 | Storage Setup | Create GCS Bronze Bucket | Create Google Cloud Storage bucket for raw API ingestion | High | Harsh | To Do | Week 1 | 2 |  |  | OSS-2
OSS-4 | API Integration | Implement Libraries.io API Client | Develop Python module to fetch project metadata from Libraries.io | High | Harsh | To Do | Week 1 | 5 |  |  | OSS-1

## Sprint Timeline
Sprint | Start Date | End Date | Focus
Week 1 |  |  | API ingestion and GCS Bronze layer setup
Week 2 |  |  | BigQuery Bronze external table and Silver transformations
Week 3 |  |  | Gold analytical views, monitoring, and documentation

## Epic Summary
Epic | Description
Project Setup | Initial configuration and environment preparation
API Integration | Connect to Libraries.io API and retrieve data
Ingestion Pipeline | Store raw API data into Bronze layer (GCS)
Data Transformation | Clean and structure data in Silver layer
Analytics | Create Gold insights for CTO decision making
Documentation | Architecture diagrams and README